August – FHFC’s workshop

on RFA 2022-103

November – Naming

Aspire 1650

2020	2022

January-April – Meetings with County Commissioners to secure NHAC site

October – Discussions with

GM on a Pompano Site

December – Discussions with Broward County on North Site property locations

May – Negotiations with County Administration on NHAC site (transportation, drainage, etc.)

November 15 – Item #72 – BOCC conveyance of property Quit Claim Deed. BOCC commits to drainage, site development agreement & transportation

June – NHAC

identified as the site

January – GM provides concept

analysis for a North Site location

June – Keith Team submits application to City of Pompano Development Review Committee

November – Broward County transfer of title approved, Pompano P&Z presentations

December 28th – Quit Claim

Deed from BOCC

December 21st – BOD Approval of LLCs – Aspire 1650

December 13th – Pompano City

Commission 2nd reading

November – Pompano City Commission 1st reading

September-December – Property site development and negotiations with County Administrators

Fla. Housing Finance Corp

City / County / Community

BP / GM

2021	2022

03/10/2023 – FHFC Notice:

Not Awarded / Not Funded

2023	2024

1/05/2023 – Quit Claim

Deed recorded

January 6 – Incorporation

of Aspire LLCs

4/10/2024 – Tax Exemption

approval from BCPA

January – FHFC Applicant

01/26/2023 – Submission

of Application to FHFC

07/01/2024 – Official Congressional Appropriations Award from Congresswoman McCormick in the amount of $850,000 announced

12/03/24 – Filed $7.5 MM HUD CoC Builds Grant

Interviews DKL / FME / GM

12/03/2023 – Item #44 –

BOCC $2.4M Capital outlay

for improvements

January – Successfully completed Phase I and Phase II Environmental Site Assessment (ESA)

01/13/25 - Successfully completed FHFC Applicant Interviews

January 21 – Submitted

Application to FHFC

March 28 – FHFC Award for Aspire 1650 Ltd.

July - Final design @ 90 Units: 8 studios; 68 1/1s; 14 2/2s

June 2023 – Three (3) Preliminary site plan designs from Architects Gallo Herbert

March – Federal Congressional Applications Submitted for Community Projects – Congressman Moskowitz and Congresswoman Cherfilus- McCormick

City/County/State/Federal

Fla. Housing Finance Corp

BP / GM

2023	2025

2025

2025

November 19 – Final Planning and Zoning Hearing – Secured Site Plan Approval

October 8 – Architectural Appearance Committee (AAC) Submittal

October 6 – DRC Resubmittal

May 16 – 1st Design of the Site Plan

April 28 – Invited to enter Credit Underwriting

May 19 – Tenant Selection Plan Approved by CUR

November 4 – AAC Hearing and approval

June 17 – Market Study Completed

June 17 – Geo Tech Agreement Signed/Submitted

January 20 – Dry Run Building Permits Submitted

January 12 – Jim Moran Anniversary Award

September 2 – Surface Water Management License Application - Submitted

August 19 – Geo Tech Final Report Received

February 18 – Carryover Agreement Approval by FHFC

February 26 – Construction bid packets released. Responses date: 04/02/2026

March 6 – South Florida Water Management District Permit Approved

September 12 – Carryover Agreement Received

October 1 – Pompano Beach Development Review (DRC) 1st Submittal

September 2 – Environmental Resources Permit Submitted

2025

2026

City/County/State/Federal

Fla. Housing Finance Corp

BP / GM